## NGHR FullPackage
No | Module / Task | Notes
1. Core Infrastructure
1 | • Multi-tenancy setup with PostgreSQL schemas
2 | • Database models and migrations
3 | • Tenant routing and middleware
4 | • Environment configuration (.env setup)
5 | • Static files and media handling
2. User Management & Authentication
6 | • Custom user model and authentication
7 | • Role-based access control (RBAC)
8 | • Permission system implementation
9 | • User groups and hierarchy
10 | • Login/logout functionality
11 | • Password reset and management
3. Company & Organization Setup
12 | • Company profile management
13 | • Department structure
14 | • Position/Job title management
15 | • Zone/Building/Floor hierarchy
16 | • Master data scripts
4. HR & Employee Management
17 | • Employee profile (personal info, documents)
18 | • Employee photo upload and management
19 | • Employment history tracking
20 | • Contract management
21 | • Probation tracking
22 | • Employee search and filtering
23 | • Employee status management (active/inactive)
24 | • Employee autocomplete component
5. ID Card Management
25 | • ID card request workflow
26 | • Card printing and generation
27 | • Card lifecycle (issue, renew, replace, return)
28 | • QR code generation
29 | • Card history and audit trail
6. Leave Management
30 | • Leave type configuration
31 | • Leave balance tracking
32 | • Leave request and approval workflow
33 | • Leave calendar view
34 | • Leave reports and analytics
7. Attendance & Timecard
35 | • Attendance marking (manual)
36 | • Fingerprint integration (back office)
37 | • Timecard Excel import template
38 | • Timecard verification UI
39 | • Cut-off date logic (20th monthly)
40 | • Attendance reports
41 | • Manual timecard fallback
8. Overtime Management
42 | • OT types (Normal ×1, Holiday ×1.5)
43 | • OT claim form
44 | • OT Excel import template
45 | • Multi-project OT tracking
46 | • HR verification workflow
47 | • OT approval workflow (Manager)
48 | • OT adjustment interface
9. Payroll System
49 | • Salary structure and components
50 | • Payroll period setup
51 | • Salary calculation engine
52 | • OT integration with payroll
53 | • Deductions and allowances
54 | • Payslip generation
55 | • Payroll summary reports
56 | • Bulk payslip generation
10. Project Management
57 | • Project creation and setup
58 | • Project team allocation
59 | • Project timeline and milestones
60 | • Project status tracking
61 | • Multi-project employee assignment
11. E-Forms System
62 | • Form builder infrastructure
63 | • Worker registration form
64 | • Document upload forms
65 | • Form validation and MRZ scanning
66 | • 6 additional form pages
67 | • Form submission workflow
12. Billing & Payments
68 | • Service charge configuration
69 | • Billing cycle management
70 | • Invoice generation
71 | • Payment recording
72 | • Payment reports
13. Document Tracking
73 | • Document type management
74 | • Document upload and storage
75 | • Document expiry tracking
76 | • Document verification workflow
14. Audit & Logging
77 | • Audit trail infrastructure
78 | • Change tracking for critical data
79 | • User activity logging
80 | • Audit reports and search
15. Dashboard & Analytics
81 | • Main dashboard layout
82 | • Employee statistics widgets
83 | • Attendance charts
84 | • Leave statistics
85 | • Payroll summary dashboard
86 | • Custom report builder
16. REST API
87 | • API authentication (JWT)
88 | • Employee endpoints
89 | • Attendance endpoints
90 | • Leave endpoints
91 | • Payroll endpoints
92 | • API documentation (Swagger)
17. Recruitment Module
93 | • Job posting management
94 | • Applicant tracking
95 | • Interview scheduling
96 | • Candidate evaluation
97 | • Offer management
18. Training & Development
98 | • Training course catalog
99 | • Training enrollment
100 | • Training attendance tracking
101 | • Certification management
102 | • Training reports
19. Performance Management
103 | • Performance review templates
104 | • Goal setting and tracking
105 | • 360-degree feedback
106 | • Performance rating system
107 | • Performance reports
20. Testing & QA
108 | • Unit test setup
109 | • Critical module testing
110 | • Integration testing
111 | • User acceptance testing (UAT)
112 | • Bug fixing
21. Deployment & DevOps
113 | • Production server setup
114 | • Database backup strategy
115 | • SSL certificate configuration
116 | • Deployment scripts
117 | • Monitoring and logging setup

## JKimPackage
No | Module / Task | Est (Days) | PIC | Notes
| 2. User Management & Authentication |  | Kanel |  | Web Applcation
6 | • Custom user model and authentication | 3 |  |  | Resource | Time Allocation | Est. | Module
7 | • Role-based access control (RBAC) | 4 |  | Staff, Worker, HRAdmin,Line Manager | Bonna | 80% | 2 Months | Payroll
10 | • Login/logout functionality | 2 |  |  | Kosal | 100% | 2 Months | HR
| 3. Company & Organization Setup |  | Kosal |  | Kanel | 20% | 2 Months | Technical Lead
12 | • Company profile management | 3
13 | • Department structure | 2 |  |  | Cost | 2000
14 | • Position/Job title management | 1
| 4. HR & Employee Management |  | Kosal |  | Mobile App
17 | • Employee profile (personal info, documents) | 2
20 | • Contract management | 3 |  |  | Kanel | 50% | 1 Month | Mobile feature
22 | • Employee search and filtering | 3
23 | • Employee status management (active/inactive) | 2 |  |  | Cost | 700
| 7. Attendance & Timecard |  | Bonna
35 | • Attendance marking (manual) | 3 |  |  | Hosting
36 | • Fingerprint integration (back office) | 4 |  |  | DP | 17$/Month
37 | • Timecard Excel import/upload template | 3
38 | • Timecard verification UI | 2
39 | • Cut-off date logic (20th monthly) | 2
40 | • Attendance reports | 3
| 8. Overtime Management |  | Bonna
42 | • OT types (Normal ×1, Holiday ×1.5) | 2
44 | • OT Excel import/upload template | 3
45 | • Multi-project OT tracking | 4
46 | • HR verification workflow | 4
47 | • OT approval workflow (Manager) | 3
48 | • OT adjustment interface | 2
| 9. Payroll System |  | Bonna
49 | • Salary structure and components | 4
50 | • Payroll period setup | 2
51 | • Salary calculation | 4
52 | • OT integration with payroll | 4
53 | • Deductions and allowances | 3
54 | • Payslip generation | 3
| 10. Project Management |  | Kanel
57 | • Project creation and setup | 3
58 | • Project team allocation | 3
59 | • Project timeline and milestones | 3
60 | • Project status tracking | 2
61 | • Multi-project employee assignment | 3
| 15. Dashboard & Analytics |  | Kanel
81 | • Main dashboard layout | 2
85 | • Payroll summary dashboard | 2
| TOTAL | 98

## Mobile
No | Module / Task | Est (Days) | PIC | Notes
1 | Time Tracking
2 | Check In / Out | 3 | Kanel
3 | Request | 5 | Kanel
4 | Shortbreak | 4 | Kanel
5 | Request leave/OT | 2 | Kanel
6 | My Team |  | Kanel
7 | View Team Status | 3 | Kanel
8 | Calendar | 2 | Kanel
9 | Schedule | 1 | Kanel
10 | Directory | 2 | Kanel
11 | Payslip | 2 | Kanel
12 | History | 3 | Kanel
13 | KPI | 3 | Kanel
14 | Manage and update progress | 2 | Kanel